## WBS_3
Work Breakdown Structure
| Mega Process | Process | Functions | sub process | sub process | sub process | Activity | sub activity | sub activity | Responsibility | Resources | Resources | Dependency | Start Date | Finish Date | Template Reference
1 | Dept. Familiarization
1.1 |  | Collect Data |  |  | ddd
1.1.1 | [6 empty] | Know Your Organization - Group,JSPL & Dept. |  |  | name | comput, laptop, |  |  | 2015-05-18 | 2015-05-18 | Available in Company
1.1.2 | [5 empty] | assadf | Layout | [6 empty] | 2015-05-18 | 2015-05-18 | Available in Company
[6 empty] | asd | Products & Customers | [6 empty] | 2015-05-18 | 2015-05-18 | Available in Company
[6 empty] | dd | Value Chain | [6 empty] | 2015-05-18 | 2015-05-18 | Available in Company
[7 empty] | Equipment and OEE - CCR Only | [6 empty] | 2015-05-18 | 2015-05-22 | Available in Company
[7 empty] | SOP - Ops,Mech,Elect,Quality | [6 empty] | 2015-05-18 | 2015-05-22 | SOP as per Company
[7 empty] | Structure | [6 empty] | 2015-05-18 | 2015-05-19 | Available in Company
[7 empty] | People – 8 Fields : Name, Qualification, Exp, Designation, Function workinging in, CTC, Preformance Score of last 2 Years, Behavioural Competency | [6 empty] | 2015-05-18 | 2015-05-18 | Available in Company
[7 empty] | IT – Hardware and Software used | [6 empty] | 2015-05-18 | 2015-05-24 | Available in Company
[7 empty] | KRA/KPI from HR | [6 empty] | 2015-05-18 | 2015-05-20 | Available in Company
[7 empty] | Manpower Cost | [6 empty] | 2015-05-18 | 2015-05-19 | Available in Company
[7 empty] | Sales Breakup per Quantity(Captive - Location wise, Market Selling- Agent/StockHouse) | [6 empty] | 2015-05-18 | 2015-05-21 | Available in Company
[7 empty] | Incentive Schemes | [6 empty] | 2015-05-18 | 2015-05-21 | Available in Company
[7 empty] | Six Month Monthly Plant Report - Covering all PPP & EPP | [6 empty] | 2015-05-18 | 2015-05-20 | Available in Company
1.2 |  | Meeting the Top 5
[7 empty] | Share WBS for Top 5 | [6 empty] | 2015-05-18 | 2015-05-18 | Template 001
[7 empty] | Share Overall Project Objective for Top 5 | [6 empty] | 2015-05-18 | 2015-05-18 | Template 002
[7 empty] | Share Overall Project Milestones for Top 5 | [6 empty] | 2015-05-18 | 2015-05-18 | Template 003
[7 empty] | Share ODIF Model for Top 5 | [6 empty] | 2015-05-18 | 2015-05-18 | Template 004
[7 empty] | Finalize Daily HOD Meeting | [6 empty] | 2015-05-18 | 2015-05-18
[7 empty] | Take Plant Round | [6 empty] | 2015-05-18 | 2015-05-18
[7 empty] | One on One with Top 5 - Issues and Concerns - Intra and Inter Dept. | [6 empty] | 2015-05-19 | 2015-05-20 | Template 005
[7 empty] | Divide Plant in 4-5 CVCP as Clear Quality and Quantiy measurement Area | [6 empty] | 2015-05-20 | 2015-05-20
2 | RMHS
2.1 |  | WAGON TIPPLER
2.1.1 |  |  | Operations

## Template 003
Project Charter
Name¦Desgn | PBOPlus¦Company
Project Name | ARJUN |  |  |  |  | Period Highlight: | 1 | Plan |  | Actual |  | % Complete |  | Actual (Delay) |  | % Complete (beyond plan)
Template No. | 2015-05-13
Template No. | 3
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
DEPARTMENT | START | DURATION | START | DURATION | COMPLETE | PERIODS
[6 empty] | 1 | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 | 8 | 9 | 10 | 11 | 12
Blast Furnace I | 1 | 2 | 0 | 0 | 0%
Blast Furnace II | 1 | 2 | 0 | 0 | 0%
SMS II | 1 | 2 | 0 | 0 | 0%
SMS III | 1 | 2 | 0 | 0 | 0%
RMHS | 1 | 2 | 0 | 0 | 0%
DRI - I | 3 | 2 | 0 | 0 | 0%
DRI - II | 3 | 2 | 0 | 0 | 0%
Plate Mill | 3 | 2 | 0 | 0 | 0%
MLSM | 3 | 2 | 0 | 0 | 0%
RUBM | 3 | 2 | 0 | 0 | 0%
Power Plant | 3 | 2 | 0 | 0 | 0%
EPS | 3 | 2 | 0 | 0 | 0%
Coal Washery | 5 | 2 | 0 | 0 | 0%
TSD | 5 | 2 | 0 | 0 | 0%
Material Management - S, CC, CDMC, EAC | 5 | 2 | 0 | 0 | 0%
Marketing Coordination & PPC | 5 | 2 | 0 | 0 | 0%
Logistics | 1 | 2 | 0 | 0 | 0%
Cement Plant & Limestone Mines | 5 | 2 | 0 | 0 | 0%
Civil | 7 | 2 | 0 | 0 | 0%
Central Services & Projects | 7 | 2 | 0 | 0 | 0%
Dolo & Lime Plants | 7 | 2 | 0 | 0 | 0%
Sinter Plants | 7 | 2 | 0 | 0 | 0%
Coke Oven | 7 | 2 | 0 | 0 | 0%
Energy Cel | 7 | 2 | 0 | 0 | 0%
Refractory | 7 | 2 | 0 | 0 | 0%
EMD | 7 | 2 | 0 | 0 | 0%
Finance & Accounts, Exice & Sales Tax | 9 | 2 | 0 | 0 | 0%
Safety & OH | 9 | 2 | 0 | 0 | 0%
SAF, Gas Facility, PGP, Oxygen Plant | 9 | 2 | 0 | 0 | 0%
HR & ES - HR, ES, IE, IETC, Horticulture, Administration, CSR, Coal, SSD, JISL, Liaison & PR | 9 | 2 | 0 | 0 | 0%
Coal Mines & Gare IV/6 | 9 | 2 | 0 | 0 | 0%
SSD | 9 | 2 | 0 | 0 | 0%
SFSS (Security) | 9 | 2 | 0 | 0 | 0%
JISL | 10 | 1 | 0 | 0 | 0%
Marketing - By Products | 10 | 1 | 0 | 0 | 0%
Internal Audit | 10 | 1 | 0 | 0 | 0%