## Sheet1
A.1 | Graphite Business Study
A.1.1 |  | Collect Data
|  |  | Know Your Organization - Group,GIL & Dept. | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Collect Overall Org. Structurture | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Products & Customers | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16 | Template G1-G13
|  |  | Value Chain | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Equipment and OEE | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | SOP - Ops,Mech,Elect,Quality | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Structure | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | People – 10 Fields* | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | IT – Hardware and Software used | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | KRA/KPI | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Manpower Cost | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Sales Breakup | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Incentive Schemes | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Six Month Monthly Plant Report - Covering all PPP & EPP | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
A.1.2 |  | Meet Top Management
|  |  | Discuss WBS with 5 Top Management Officials | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Revise WBS as per inputs/ availability of resources | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Share the Revised WBS with the Top Management | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Share Overall Project Milestones for Top 5 | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Share ODIF Model for Top 5 | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
|  |  | Finalize Review Meeting Schedule and Agenda | PBO+ Team | GIL Cordinator | 24/10/16 | 25/10/16
A.2 | OMQ Integration- RM to FG
A.2.1 |  | AS-IS Process Mapping
|  |  | Meet Process Owner/HOD and communicate Project Objective | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Share Project Milestone/Methodology and WBS | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Fix up time for Daily update/review meeting with HOD | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Process Familarization | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Process Flow Mapping with Input/output and supporting process hierarchy | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16 | Analysis 4, Analysis 5, Analysis 10, Template 1-5
|  |  | Department/Resources mapping at each stage of Process | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Identify Process Sample | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Collect Process Frequency data | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Video Film Process sample to collect process activity duration,team size | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Map all Exceptions of the process | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Map all risks associated with the process | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Data Collection & Interviews | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Confirm validity of data with process owner | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
A.2.2 |  | NVA Identification and Elimination
|  |  | Identify and Classify NVA observed in the existing process | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Identify Solutions to eliminate NVA | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Calculate Time, Resource, Cost saving assessment by elimination of NVA | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Identify Risk Associated with proposed process | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
A.2.3 |  | Automation
|  |  | Identify and Classify NVA observed in the existing process | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Identify Solutions to eliminate NVA | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Calculate cost investment of Automation application | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Calculate Time, Resource, Cost saving assessment by elimination of NVA | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Identify Risk Associated with proposed process | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
A.2.4 |  | To Be Process
|  |  | Draw To-Be Process flow | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Define clear rules of execution | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Define Frequency,Team Size and process duration along with Limits | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Present the To-be Process to Respective process owner | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
A.2.5 |  | Proposed Structure
|  |  | Assess the need of multi-skill, multi-functional training of the people engaged in the process | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Calulate workload for To-Be process | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Calculate Manpower requirement based on this workload | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Assess the Gap in As-Is and To- Be people skill | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Identify people fitment in Three-layered structure | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Identify new roles and responsibilities if any | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
A.2.6 |  | Financial Gain
|  |  | Calculate Financial Gain through Manpower Rationalization | PBO+ Team | GIL Cordinator | 2016-04-10 | 2016-06-10
|  |  | Calculate Financial Gain through Process improvement | PBO+ Team | GIL Cordinator | 2016-04-10 | 2016-06-10
|  |  | Communicate the gains along with implementation pre-requisites to respective process owner | PBO+ Team | GIL Cordinator | 2016-04-10 | 2016-06-10
A.3 | Marketing & Sales ( Prospect to Order, Order to Cash)
A.3.1 |  | AS-IS Process Mapping
|  |  | Meet Process Owner/HOD and communicate Project Objective | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Share Project Milestone/Methodology and WBS | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Fix up time for Daily update/review meeting with HOD | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Process Familarization | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Process Flow Mapping with Input/output and supporting process hierarchy | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16 | Analysis 1, Analysis 6-9
|  |  | Department/Resources mapping at each stage of Process | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Identify Process Sample | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Collect Process Frequency data | PBO+ Team | GIL Cordinator | 25/10/16 | 27/10/16
|  |  | Video Film Process sample to collect process activity duration,team size | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Map all Exceptions of the process | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Map all risks associated with the process | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Data Collection & Interviews | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Confirm validity of data with process owner | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
A.3.2 |  | NVA Identification and Elimination
|  |  | Identify and Classify NVA observed in the existing process | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Identify Solutions to eliminate NVA | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Calculate Time, Resource, Cost saving assessment by elimination of NVA | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
|  |  | Identify Risk Associated with proposed process | PBO+ Team | GIL Cordinator | 28/10/16 | 2016-04-10
A.3.3 |  | Automation
|  |  | Identify and Classify NVA observed in the existing process | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Identify Solutions to eliminate NVA | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Calculate cost investment of Automation application | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Calculate Time, Resource, Cost saving assessment by elimination of NVA | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Identify Risk Associated with proposed process | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
A.3.4 |  | To Be Process
|  |  | Draw To-Be Process flow | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Define clear rules of execution | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Define Frequency,Team Size and process duration along with Limits | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Present the To-be Process to Respective process owner | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
A.3.5 |  | Proposed Structure
|  |  | Assess the need of multi-skill, multi-functional training of the people engaged in the process | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Calulate workload for To-Be process | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Calculate Manpower requirement based on this workload | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Assess the Gap in As-Is and To- Be people skill | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Identify people fitment in Three-layered structure | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
|  |  | Identify new roles and responsibilities if any | PBO+ Team | GIL Cordinator | 2016-02-10 | 2016-04-10
A.3.6 |  | Financial Gain
|  |  | Calculate Financial Gain through Manpower Rationalization | PBO+ Team | GIL Cordinator | 2016-04-10 | 2016-06-10
|  |  | Calculate Financial Gain through Process improvement | PBO+ Team | GIL Cordinator | 2016-04-10 | 2016-06-10
|  |  | Communicate the gains along with implementation pre-requisites to respective process owner | PBO+ Team | GIL Cordinator | 2016-04-10 | 2016-06-10