## Sheet1
Plot Issues
S. No | Issues | Status | Status(12-12-16)
1 | Project performance graph/score incorrect. | Not Resolved | Not Resolved
2 | ODIF Score incorrect.
3 | Problem in import the file. | Not Resolved
4 | Not able to save/submit the WBS | Resolved | Resolved
5 | Mega Process column gets activated. | Not Resolved
6 | Unique code is visible only after saving the WBS./ numbering starts after submittion. | Not Resolved
7 | Drop down box for dependency is visible after saving the WBS. | Not Resolved
8 | File name is not displayed. | Not Resolved
9 | ODIF mail not on time/ don’t get any notification whenever anyone assigned a project | Not Resolved
10 | In my project sometime other projects are also visible. | Resolved | Resolved
11 | There should be confirmation before deletion. | Not Resolved | Resolved
12 | No option for recovery of data/ Undo |  | Not Resolved
13 | In resources column, no option for adjustment of data.
14 | No notification for new work
15 | deleted project, emails are coming
16 | Activity date should not be greater than project date
17 | Dependency can be more than one.
18 | There is no delete button in templte
19 | In import option, file can only be uploaded in CSV format
20 | We cannot add the Person as a team member who is assigned a project manager id
21 | we can remove add wbs button and have row below headers
22 | can delete mega process and process column
23 | WBS duplication .
24 | Project manager can delete and edit role of team member.
25 | we can submit WBS without filling all the column.