## Moolchand WBS
Diagnostic Study - Work Breakdown Structure
Sr No. | L1 | L2 | L3 | RC | Start Date | End Date | Status
1 | Occupancy |  | Planned occupancy level(Atleast 1 year data) | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Actual occupancy level(Atleast 1 year data) | Moolchand | 2016-12-01 | 2016-12-02
|  |  | OPD to IPD conversion rate(Atleast 1 year data) | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Actual occupancy level ward wise(Atleast 1 year data) | Moolchand | 2016-12-01 | 2016-12-02
2 | Customer Parameters
|  |  | Customer Delight Index score if available | Moolchand | 2016-12-01 | 2016-12-01
2.1 |  | Current customer segmentation
|  |  | Ratio of domestic : international patients | Moolchand | 2016-12-01 | 2016-12-01
|  |  | Percentage of local walkin patients | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Percentage of local referral patients | Moolchand | 2016-12-01 | 2016-12-02
|  |  | i) Local patients within Delhi | Moolchand | 2016-12-01 | 2016-12-02
|  |  | ii) Local patients outside Delhi | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Percentage of Cash patients | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Percentage of TPA/Govt patients | Moolchand | 2016-12-01 | 2016-12-02
Percentage of revenue from Cash, Corporate and international patients
2.2 |  | Patient admission break up speciality wise (last 1 year)
|  |  | Oncology | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Fertility & IVF | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Cardiology | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Orthopedics | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Nephrology | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Gynaecology | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Endocrinology | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Neurology and neurosurgery | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Transplants | Moolchand | 2016-12-01 | 2016-12-02
|  |  | spine surgery | Moolchand | 2016-12-01 | 2016-12-02
3 | Patient parameters |  | Patient centric data already with the hospital:
|  |  | Patient feedback | Moolchand | 2016-12-01 | 2016-12-02
|  |  | NRS Score | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Doctor feedback | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Any other patient satisfaction related data | Moolchand | 2016-12-01 | 2016-12-02
3.1 |  | Current customers' feedback | 30 Patients from OPD | PBO | 2016-12-02 | 2016-12-03
|  |  | 20 Patients from IPD | PBO | 2016-12-02 | 2016-12-04
3.2 |  | Ex-customers' feedback | 20 patients who were discharged in last 30 days | PBO | 2016-12-02 | 2016-12-04
|  |  | 20 patients who were discharged in last 6-12 months | PBO | 2016-12-02 | 2016-12-04
4 | Process parameters
|  | Service parameters important for patients | Ranking of parameters in terms of importance level | PBO | 2016-12-02 | 2016-12-05
|  | IPD processes | Nursing and housekeeping deployment | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Documentation | Moolchand | 2016-12-01 | 2016-12-02
|  |  | Nursing daily activity mapping | Moolchand | 2016-12-01 | 2016-12-04
|  | OPD processes | Hospital data (if available) on waiting times for:
|  |  | Billing | Moolchand | 2016-12-02 | 2016-12-03
|  |  | report Collection | Moolchand | 2016-12-02 | 2016-12-03
|  |  | meeting doctor | Moolchand | 2016-12-02 | 2016-12-03
|  |  | Validation of data | PBO | 2016-12-03 | 2016-12-05
5 | Competition information | Business development | Understanding brand image of Moolchand among referral doctors'. | PBO | 2016-12-02 | 2016-12-05
|  |  | Data regarding poaching of patients by other hospitals (if any) | Moolchand | 2016-12-02 | 2016-12-05